## Project schedule
| TNB Project | [5 empty] | Project start: | [5 empty] | 2025-04-01
[7 empty] | Display week: | [5 empty] | 1
[7 empty] | Week 1 |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12 |  |  |  |  | Week 13 |  |  |  |  | Week 14 |  |  |  |  | Week 15 |  |  |  |  | Week 16
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2025-04-01 to 2025-07-18
 | time axis 2025-04-01 to 2025-07-18
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Initiation
| Kickoff Meeting on Collaboration | Retragreen / TNB | 0% | 2025-04-01 | 2025-04-08 | 8
| Define Scope and Responsibility | Retragreen / TNB | 0% | 2025-04-04 | 2025-04-07 | 4
| NDA and Commercial Term and Agreement | Retragreen / TNB | 0% | 2025-04-07 | 2025-04-10 | 4
| Develop charter : POC Scope and Evaluation | Retragreen / TNB | 0% | 2025-04-10 | 2025-04-13 | 4
| Set up team for Project Execution | Retragreen / TNB | 0% | 2025-04-13 | 2025-04-16 | 4
Planning and design
| Create schedule for Identified POC Project | Retragreen / TNB | 0% | 2025-04-16 | 2025-04-19 | 4
| Conduct Retragreen Building and BMS Information Collection (Stage1) | TNB | 0% | 2025-04-19 | 2025-04-22 | 4
| Conduct System Basic Data for Project Connectivity Identification | TNB | 0% | 2025-04-22 | 2025-04-25 | 4
| Evaluation of Savings Potential and Achievable Deliverables | Retragreen | 0% | 2025-04-25 | 2025-04-28 | 4
| Confirmation of Connectivity and Risk Assessment | TNB | 0% | 2025-04-28 | 2025-05-01 | 4
Execution
| Execute tasks (a) Installation of Gateway (b) Connectivity for Data Acquistion | TNB | 0% | 2025-05-01 | 2025-05-04 | 4
| Monitor progress (a) Confirmation of Data Read/ Write (b) Preparation for Data Optimisation | Retragreen | 0% | 2025-05-04 | 2025-05-07 | 4
| Manage Resources (a) Data Optimisation Trial (b) Monitor for any Issue | Retragreen | 0% | 2025-05-07 | 2025-05-10 | 4
| Provide updates (a) Data Optimisation (Step1) (b) Daily Monitoring Results and Issues | Retragreen | 0% | 2025-05-10 | 2025-05-13 | 4
| Testing and validation (a) Live Test (for one month) and Feedback from Site | Retragreen/ TNB | 0% | 2025-05-13 | 2025-05-16 | 4