## Project schedule
| KLIA District Cooling System | [5 empty] | Project start: | [5 empty] | 2025-04-01
[7 empty] | Week 1 |  |  |  | Week 2 |  |  |  |  | Week 3 |  |  |  |  | Week 4 |  |  |  |  | Week 5 |  |  |  |  | Week 6 |  |  |  |  | Week 7 |  |  |  |  | Week 8 |  |  |  |  | Week 9 |  |  |  |  | Week 10 |  |  |  |  | Week 11 |  |  |  |  | Week 12 |  |  |  |  | Week 13 |  |  |  |  | Week 14 |  |  |  |  | Week 15 |  |  |  |  | Week 16 |  |  |  |  | Week 17 |  |  |  |  | Week 18 |  |  |  |  | Week 19 |  |  |  |  | Week 20 |  |  |  |  | Week 20 |  |  |  |  | Week 20 |  |  |  |  | Week 20 |  |  |  |  | Week 20 |  |  |  |  | Week 20 |  |  |  |  | Week 20 |  |  |  |  | Week 20
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2025-04-01 to 2025-10-03
 | time axis 2025-04-01 to 2025-10-03
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Phase 1 Initiation
1 | 1.1 Kick-off Meeting for Collaboration | Retragreen / TNB | 0% | 2025-04-01 | 2025-04-08 | 7
| 1.2 Define Scope and Responsibilities | Retragreen / TNB | 0% | 2025-04-09 | 2025-04-16 | 7
| 1.3 NDA and Commercial Terms and Agreement | Retragreen / TNB | 0% | 2025-04-17 | 2025-04-24 | 7
| 1.4 Develop Charter: POC Scope and Evaluation | Retragreen / TNB | 0% | 2025-04-25 | 2025-05-02 | 7
| 1.5 Set-up Team for Project Execution | Retragreen / TNB | 0% | 2025-05-03 | 2025-05-10 | 7
Phase 2 Planning and Design
| 2.1 Create Schedule for Identified POC Project | Retragreen / TNB | 0% | 2025-05-11 | 2025-05-18 | 7
| 2.2 Conduct Retragreen Building and BMS Information Collection (Site Visit) | Retragreen / TNB | 0% | 2025-05-19 | 2025-05-26 | 7
| 2.3 Conduct System Basic Data Collection for Project Connectivity Identification (Site Visit) | Retragreen / TNB | 0% | 2025-05-27 | 2025-06-03 | 7
| 2.4 Evaluation of Savings Potential and Achievable Deliverables | Retragreen / TNB | 0% | 2025-06-04 | 2025-06-11 | 7
| 2.5 Progress Review Meeting Prior to Execution | Retragreen / TNB | 0% | 2025-06-12 | 2025-06-19 | 7
Phase 3 Execution
| 3.1 Execute Tasks (a) Installation of Gateway (b) Connectivity for Data Acquistion | Retragreen / TNB | 0% | 2025-06-20 | 2025-07-04 | 14
| 3.2 Monitor Progress (a) Confirmation of Data Read/ Write (b) Preparation for Data Optimisation | Retragreen / TNB | 0% | 2025-07-05 | 2025-07-19 | 14
| 3.3 Manage Resources (a) Data Optimisation Trial (b) Monitor for Any Issues | Retragreen / TNB | 0% | 2025-07-20 | 2025-08-03 | 14
| 3.4 Provide updates (a) Data Optimisation (Simulation) (b) Daily Monitoring Results and Issues | Retragreen / TNB | 0% | 2025-08-04 | 2025-08-18 | 14
| 3.5 Testing and Validation (a) Live Test and Feedback from Site | Retragreen / TNB | 0% | 2025-08-19 | 2025-09-16 | 28
| 3.6 Final Acceptance and Handover | Retragreen / TNB | 0% | 2025-09-18 | 2025-09-20 | 2